## Slide 1: IMPROVING EMPLOYEE INVOLVEMENT IN UNDERTAKINGS IN ANTICIPATION AND MANAGEMENT OF CHANGE DRIVEN BY GREEN TRANSITION – GTA
Sharing of the project objectives, expected results, work programme, deadlines;
Planning the dates and content of the project events and outputs to be produced, division of tasks between the Partners.
Online Steering Committee Meeting, 01.02.2024

## Slide 2: General objective
The overarching objective of this project is to build the capacity of stakeholders to use information, consultation and participation tools in the workplace, ensuring effective engagement of workers in decision-making processes related to the green transition and taking into account their interests, thereby addressing the second priority of supporting worker involvement in the anticipation and management of change and the prevention and resolution of disputes in the event of various forms of restructuring.

## Slide 3: CONSORTIUM (1/2)
Leader: ALL POLAND ALLIANCE OF TRADE UNIONS – OPZZ (PL) Partners: VORMING EN ACTIE (BE) GENERAL WORKERS’ UNION – GWU (MT)
THE MALTA CHAMBER OF COMMERCE AND ENTERPRISE ASSOCIATION – MCOC (MT)
FEDERATION OF POLISH ENTREPRENEURS - FPP (PL)

## Slide 4: CONSORTIUM (2/2)
Partners:
THE ASSOTIATION OF TRADE UNIONS OF LVIV REGION – ATULR (UA)
CONFEDERAZIONE GENERALE ITALIANA DEL LAVORO – CGIL (IT)
SVAZ PODNIKATELU VE STAVEBNICTVI – SPS (CZ)
LGEMEEN CHRISTELIJK VAKVERBOND VAN BELGIE - ACV-CSC (BE)

## Slide 5: DURATION: 1 December 2023 – 31 July 2025 Exchange of good practices and experiences Advisers Network EGWPAN Action plan of the EGWPAN network Online competence courses OER’s digital platform National online trainings for workers representatives Green Change Management Action Plan For Inclusive Green Transition

## Slide 6: WORK PACKAGES
WP1 – Project management and coordination; WP2 – Development of European Green Worker – Participation Advisers Network (EGWPAN);
WP3 - Capacity building;
WP4 - Communication and Dissemination Cluster.

## Slide 7: WP1 – Project management and coordination (1/2) (01.12.2023 – 31.07.2025)
Responsible Partner: OPZZ
Objectives:
Ensure the sound administrative and financial management of the project;
Ensure the risk-management and mitigation;
Coordination and monitoring of the work among the WP Leaders;
Delivering the reporting of the project both narrative and financial to the EC;
Ensure the stakeholder engagement and achievement of the project objectives.

## Slide 8: WP1 – Project management and coordination (2/2) (01.12.2023 – 31.07.2025)
Responsible Partner: OPZZ
Deliverables:
Online Steering Committee Meeting – OPZZ (1 month);
Final External Evaluation - OPZZ (20 month);
Project visual identity - OPZZ (1 month);
Project interim/final report narrative and financial reports - OPZZ (10, 20 month).

## Slide 9: WP2 – Development of European Green Worker – Participation Advisers Network (EGWPAN) (1/2) (01.01.2024 – 31.10.2024)
Responsible Partners: GWU
Objectives:
Building the capacity of the workers and employers’ representatives via capacity building and skills development actions by implementing European Green Worker-Participation Advisers Network (EGWPAN);
Development of the action plan of the network;
3 online networking meetings (in English);
Face-to-face Competence course (2 modules);
Online competence course (2 Modules);
Preparation of OERs.

## Slide 10: WP2 – Development of European Green Worker – Participation Advisers Network (EGWPAN) (2/2) (01.01.2024 – 31.10.2024)
Responsible Partners: GWU
Deliverables:
Development of the action plan of the EGWPAN network - OPZZ (4 month);
3 online networking meetings (in English) – GWU (9 month);
Face-to-face Competence course (2 modules) - OPZZ (5 month);
Online competence course (2 Modules) – GWU (7 month);
OERs – MCOC (10 month).

## Slide 11: WP3 – Capacity building (1/2) (31.10.2024-30.04.2025)
Responsible Partner: FPP
Objectives:
To build the capacity of the social partners to realise their right to information, consultation and participation, familiarize them with the relevant EU legislation and support peer learning on these issues by the delivery in M10-M17 the end of the project the EGWPAN agile green change management course for workers’ representatives;
Testing the course: national online trainings for workers’ representatives (2 days per country);
Development of the e-learning platform (OER).

## Slide 12: WP3 – Capacity building (2/2) (31.10.2024-30.04.2025)
Responsible Partner: FPP
Deliverables:
EGWPAN agile green change management course modules - 4 modules – FPP (12 month);
National online trainings for workers’ representatives (12 days of training in 6 countries) – FPP (13 month);
e-learning platform (OER) and Online Trainings with the possibility to issue a certificate – OPZZ (17 month).

## Slide 13: WP4 – Communication and Dissemination Cluster (1/2) (01.02.2025 – 30.04.2025)
Responsible Partner: OPZZ
Objectives:
To raise the awareness on the green transition and participatory mechanisms, relevant EU laws and policies among target groups by disseminating information about outcomes and outputs of the project. This will be done by delivering a comprehensive dissemination campaign for spreading the project results as much as possible through different dissemination tools. The WP aims will be achieved before the project ends (and due to the sustainability strategy will also continue after it ends).

## Slide 14: WP4 – Communication and Dissemination Cluster (2/2) (01.02.2025 – 30.04.2025)
Responsible Partner: OPZZ
Deliverables:
Online EU-level looking forward seminar – OPZZ (18 month);
Green Change Management Action Plan For Inclusive Green Transition – OPZZ (18 month);
Video promoting the work of the of European Green Worker-Participation Advisers Network (EGWPAN) – OPZZ (19 month);
PCDP outputs – newsletters, pictures, ads, article – OPZZ (20 month).

## Slide 15: For further information: Anna Fastyn – Project Officer +48 797 556 883/ fastyn@opzz.org.pl THANK YOU